## Personas
Sunhaven Care Workforce Personas | Sunhaven Care Workforce Personas | Sunhaven Care Workforce Personas | Sunhaven Care Workforce Personas | Sunhaven Care Workforce Personas | Sunhaven Care Workforce Personas | Sunhaven Care Workforce Personas | Sunhaven Care Workforce Personas | Sunhaven Care Workforce Personas | Sunhaven Care Workforce Personas
All identities and records in this workbook are synthetic test data created solely for academic demonstration. No real employee, resident, medical, university, password, token, or MFA-secret data is used. | All identities and records in this workbook are synthetic test data created solely for academic demonstration. No real employee, resident, medical, university, password, token, or MFA-secret data is used. | All identities and records in this workbook are synthetic test data created solely for academic demonstration. No real employee, resident, medical, university, password, token, or MFA-secret data is used. | All identities and records in this workbook are synthetic test data created solely for academic demonstration. No real employee, resident, medical, university, password, token, or MFA-secret data is used. | All identities and records in this workbook are synthetic test data created solely for academic demonstration. No real employee, resident, medical, university, password, token, or MFA-secret data is used. | All identities and records in this workbook are synthetic test data created solely for academic demonstration. No real employee, resident, medical, university, password, token, or MFA-secret data is used. | All identities and records in this workbook are synthetic test data created solely for academic demonstration. No real employee, resident, medical, university, password, token, or MFA-secret data is used. | All identities and records in this workbook are synthetic test data created solely for academic demonstration. No real employee, resident, medical, university, password, token, or MFA-secret data is used. | All identities and records in this workbook are synthetic test data created solely for academic demonstration. No real employee, resident, medical, university, password, token, or MFA-secret data is used. | All identities and records in this workbook are synthetic test data created solely for academic demonstration. No real employee, resident, medical, university, password, token, or MFA-secret data is used.
employeeId | displayName | userPrincipalName | employmentType | jobRole | facility | managerEmployeeId | startDate | endDate | status
SC1001 | Mia Carter (TEST) | mia.carter@rifat011002gmail.onmicrosoft.com | Permanent | CareWorker | Sydney | SC1003 | 2026-07-01 |  | Active
SC1002 | Noah Singh (TEST) | noah.singh@rifat011002gmail.onmicrosoft.com | Permanent | Nurse | Sydney | SC1003 | 2026-07-02 |  | Active
SC1003 | Ava Chen (TEST) | ava.chen@rifat011002gmail.onmicrosoft.com | Permanent | Manager | Sydney |  | 2026-07-03 |  | Active
SC1004 | Liam Brooks (TEST) | liam.brooks@rifat011002gmail.onmicrosoft.com | Agency | AgencyWorker | Sydney | SC1003 | 2026-08-01 | 2026-08-20 | Active
SC1005 | Zoe Martin (TEST) | zoe.martin@rifat011002gmail.onmicrosoft.com | Contractor | Auditor | HeadOffice |  | 2026-07-05 | 2026-08-31 | Active
SC1006 | Ethan Khan (TEST) | ethan.khan@rifat011002gmail.onmicrosoft.com | Permanent | CareWorker | Sydney | SC1003 | 2026-07-06 | 2026-08-05 | Leaving
SC1007 | Olivia Reed (TEST) | olivia.reed@rifat011002gmail.onmicrosoft.com | Permanent | IAMOperator | HeadOffice |  | 2026-07-07 |  | Active
SC1008 | Isabella Green (TEST) | isabella.green@rifat011002gmail.onmicrosoft.com | Permanent | CareWorker | Sydney | SC1003 | 2026-08-07 |  | Active
SC1009 | Daniel Ortiz (TEST) | daniel.ortiz@rifat011002gmail.onmicrosoft.com | Permanent | CareWorker | Sydney | SC1003 | 2026-07-08 | 2026-08-01 | Inactive
SC1010 | Ruby Evans (TEST) | ruby.evans@rifat011002gmail.onmicrosoft.com | Agency | AgencyWorker | Sydney | SC1003 | 2026-07-01 | 2026-07-31 | Inactive

## Test Residents
Sunhaven Care Test Residents | Sunhaven Care Test Residents | Sunhaven Care Test Residents | Sunhaven Care Test Residents | Sunhaven Care Test Residents | Sunhaven Care Test Residents
All resident records are fictional and labelled as synthetic test data. AssignedEmployeeIds defines the worker-to-resident relationship used by RBAC tests. | All resident records are fictional and labelled as synthetic test data. AssignedEmployeeIds defines the worker-to-resident relationship used by RBAC tests. | All resident records are fictional and labelled as synthetic test data. AssignedEmployeeIds defines the worker-to-resident relationship used by RBAC tests. | All resident records are fictional and labelled as synthetic test data. AssignedEmployeeIds defines the worker-to-resident relationship used by RBAC tests. | All resident records are fictional and labelled as synthetic test data. AssignedEmployeeIds defines the worker-to-resident relationship used by RBAC tests. | All resident records are fictional and labelled as synthetic test data. AssignedEmployeeIds defines the worker-to-resident relationship used by RBAC tests.
residentId | displayName | facility | classification | dataLabel | assignedEmployeeIds
RTEST001 | Test Resident Alpha | Sydney | Standard | SYNTHETIC TEST DATA | SC1001, SC1004
RTEST002 | Test Resident Beta | Sydney | Restricted | SYNTHETIC TEST DATA | SC1002
RTEST003 | Test Resident Gamma | Brisbane | Standard | SYNTHETIC TEST DATA

## RBAC_Matrix_v1.0
Sunhaven Care RBAC Matrix v1.0 | Sunhaven Care RBAC Matrix v1.0 | Sunhaven Care RBAC Matrix v1.0 | Sunhaven Care RBAC Matrix v1.0 | Sunhaven Care RBAC Matrix v1.0 | Sunhaven Care RBAC Matrix v1.0 | Sunhaven Care RBAC Matrix v1.0 | Sunhaven Care RBAC Matrix v1.0 | Sunhaven Care RBAC Matrix v1.0
Owner: IAM Project Owner ¦ Status: Approved for MVP implementation ¦ Green = ALLOW ¦ Red = DENY ¦ Amber = CONDITIONAL | Owner: IAM Project Owner ¦ Status: Approved for MVP implementation ¦ Green = ALLOW ¦ Red = DENY ¦ Amber = CONDITIONAL | Owner: IAM Project Owner ¦ Status: Approved for MVP implementation ¦ Green = ALLOW ¦ Red = DENY ¦ Amber = CONDITIONAL | Owner: IAM Project Owner ¦ Status: Approved for MVP implementation ¦ Green = ALLOW ¦ Red = DENY ¦ Amber = CONDITIONAL | Owner: IAM Project Owner ¦ Status: Approved for MVP implementation ¦ Green = ALLOW ¦ Red = DENY ¦ Amber = CONDITIONAL | Owner: IAM Project Owner ¦ Status: Approved for MVP implementation ¦ Green = ALLOW ¦ Red = DENY ¦ Amber = CONDITIONAL | Owner: IAM Project Owner ¦ Status: Approved for MVP implementation ¦ Green = ALLOW ¦ Red = DENY ¦ Amber = CONDITIONAL | Owner: IAM Project Owner ¦ Status: Approved for MVP implementation ¦ Green = ALLOW ¦ Red = DENY ¦ Amber = CONDITIONAL | Owner: IAM Project Owner ¦ Status: Approved for MVP implementation ¦ Green = ALLOW ¦ Red = DENY ¦ Amber = CONDITIONAL
Role | ViewAssignedResident | ViewFacilityResidents | AddCareNote | EditClinicalNote | ExportFacilityData | ApproveAccessReview | RunJMLWorkflow | ViewAuditEvidence
CareWorker | ALLOW | DENY | ALLOW | DENY | DENY | DENY | DENY | DENY
Nurse | ALLOW | DENY | ALLOW | ALLOW | DENY | DENY | DENY | DENY
Manager | ALLOW | ALLOW | DENY | DENY | ALLOW | ALLOW | DENY | ALLOW
AgencyWorker | CONDITIONAL | DENY | CONDITIONAL | DENY | DENY | DENY | DENY | DENY
Auditor | DENY | DENY | DENY | DENY | DENY | DENY | DENY | ALLOW
IAMOperator | DENY | DENY | DENY | DENY | DENY | DENY | ALLOW | ALLOW
AgencyWorker access is allowed only when status is Active, the test date is between startDate and endDate, the worker facility matches the resident facility, and the resident is assigned to the worker. | AgencyWorker access is allowed only when status is Active, the test date is between startDate and endDate, the worker facility matches the resident facility, and the resident is assigned to the worker. | AgencyWorker access is allowed only when status is Active, the test date is between startDate and endDate, the worker facility matches the resident facility, and the resident is assigned to the worker. | AgencyWorker access is allowed only when status is Active, the test date is between startDate and endDate, the worker facility matches the resident facility, and the resident is assigned to the worker. | AgencyWorker access is allowed only when status is Active, the test date is between startDate and endDate, the worker facility matches the resident facility, and the resident is assigned to the worker. | AgencyWorker access is allowed only when status is Active, the test date is between startDate and endDate, the worker facility matches the resident facility, and the resident is assigned to the worker. | AgencyWorker access is allowed only when status is Active, the test date is between startDate and endDate, the worker facility matches the resident facility, and the resident is assigned to the worker. | AgencyWorker access is allowed only when status is Active, the test date is between startDate and endDate, the worker facility matches the resident facility, and the resident is assigned to the worker. | AgencyWorker access is allowed only when status is Active, the test date is between startDate and endDate, the worker facility matches the resident facility, and the resident is assigned to the worker.
Active-agency example: SC1004 ¦ employmentType: Agency ¦ facility: Sydney ¦ startDate: 2026-08-01 ¦ endDate: 2026-08-20 ¦ status: Active | Active-agency example: SC1004 ¦ employmentType: Agency ¦ facility: Sydney ¦ startDate: 2026-08-01 ¦ endDate: 2026-08-20 ¦ status: Active | Active-agency example: SC1004 ¦ employmentType: Agency ¦ facility: Sydney ¦ startDate: 2026-08-01 ¦ endDate: 2026-08-20 ¦ status: Active | Active-agency example: SC1004 ¦ employmentType: Agency ¦ facility: Sydney ¦ startDate: 2026-08-01 ¦ endDate: 2026-08-20 ¦ status: Active | Active-agency example: SC1004 ¦ employmentType: Agency ¦ facility: Sydney ¦ startDate: 2026-08-01 ¦ endDate: 2026-08-20 ¦ status: Active | Active-agency example: SC1004 ¦ employmentType: Agency ¦ facility: Sydney ¦ startDate: 2026-08-01 ¦ endDate: 2026-08-20 ¦ status: Active | Active-agency example: SC1004 ¦ employmentType: Agency ¦ facility: Sydney ¦ startDate: 2026-08-01 ¦ endDate: 2026-08-20 ¦ status: Active | Active-agency example: SC1004 ¦ employmentType: Agency ¦ facility: Sydney ¦ startDate: 2026-08-01 ¦ endDate: 2026-08-20 ¦ status: Active | Active-agency example: SC1004 ¦ employmentType: Agency ¦ facility: Sydney ¦ startDate: 2026-08-01 ¦ endDate: 2026-08-20 ¦ status: Active

## RBAC_Decision_Log
Sunhaven Care RBAC Decision Log | Sunhaven Care RBAC Decision Log | Sunhaven Care RBAC Decision Log | Sunhaven Care RBAC Decision Log
Version: 1.0 ¦ Status: Approved for MVP implementation ¦ Owner: IAM Project Owner ¦ Approval date: 2026-08-06 | Version: 1.0 ¦ Status: Approved for MVP implementation ¦ Owner: IAM Project Owner ¦ Approval date: 2026-08-06 | Version: 1.0 ¦ Status: Approved for MVP implementation ¦ Owner: IAM Project Owner ¦ Approval date: 2026-08-06 | Version: 1.0 ¦ Status: Approved for MVP implementation ¦ Owner: IAM Project Owner ¦ Approval date: 2026-08-06
Permission | Allowed roles | Business reason | Approving owner
ViewAssignedResident | CareWorker, Nurse, Manager, AgencyWorker | Workers require assigned records to provide authorised care | Facility Manager
ViewFacilityResidents | Manager | Manager oversees operations within their facility | Data Owner
AddCareNote | CareWorker, Nurse, AgencyWorker | Care providers must record delivered care | Facility Manager
EditClinicalNote | Nurse | Clinical corrections require clinical responsibility | Clinical Data Owner
ExportFacilityData | Manager | Required for authorised facility reporting | Data Owner
ApproveAccessReview | Manager | Managers confirm whether their workers still need access | IAM Owner
RunJMLWorkflow | IAMOperator | Identity staff perform approved lifecycle changes | IAM Owner
ViewAuditEvidence | Manager, Auditor, IAMOperator | Required for assurance, investigation and compliance | Compliance Owner
CareWorker, Nurse, Manager, AgencyWorker and Auditor are application business roles and receive no Microsoft Entra administrative role. IAMOperator receives only approved limited user and group administration roles. Global Administrator is reserved for initial setup and emergencies. | CareWorker, Nurse, Manager, AgencyWorker and Auditor are application business roles and receive no Microsoft Entra administrative role. IAMOperator receives only approved limited user and group administration roles. Global Administrator is reserved for initial setup and emergencies. | CareWorker, Nurse, Manager, AgencyWorker and Auditor are application business roles and receive no Microsoft Entra administrative role. IAMOperator receives only approved limited user and group administration roles. Global Administrator is reserved for initial setup and emergencies. | CareWorker, Nurse, Manager, AgencyWorker and Auditor are application business roles and receive no Microsoft Entra administrative role. IAMOperator receives only approved limited user and group administration roles. Global Administrator is reserved for initial setup and emergencies.

## Change_Log
Sunhaven Care IAM Design Change Log | Sunhaven Care IAM Design Change Log | Sunhaven Care IAM Design Change Log | Sunhaven Care IAM Design Change Log
Version | Date | Change | Approved by
v1.0 | 2026-08-06 | Initial least-privilege RBAC baseline | IAM Project Owner
v1.1 | 2026-08-07 | Corrected personas, test identities, JML rules, traceability wording and evidence formulas | IAM Project Owner

## JML_Workflow_Spec
Sunhaven Care JML Workflow Specification | Sunhaven Care JML Workflow Specification | Sunhaven Care JML Workflow Specification | Sunhaven Care JML Workflow Specification | Sunhaven Care JML Workflow Specification | Sunhaven Care JML Workflow Specification
Version: 1.0 ¦ Status: Approved for MVP implementation ¦ Owner: IAM Project Owner ¦ Date: 2026-08-07 | Version: 1.0 ¦ Status: Approved for MVP implementation ¦ Owner: IAM Project Owner ¦ Date: 2026-08-07 | Version: 1.0 ¦ Status: Approved for MVP implementation ¦ Owner: IAM Project Owner ¦ Date: 2026-08-07 | Version: 1.0 ¦ Status: Approved for MVP implementation ¦ Owner: IAM Project Owner ¦ Date: 2026-08-07 | Version: 1.0 ¦ Status: Approved for MVP implementation ¦ Owner: IAM Project Owner ¦ Date: 2026-08-07 | Version: 1.0 ¦ Status: Approved for MVP implementation ¦ Owner: IAM Project Owner ¦ Date: 2026-08-07
Authoritative source: Approved workforce CSV ¦ Stable identity key: employeeId | Authoritative source: Approved workforce CSV ¦ Stable identity key: employeeId | Authoritative source: Approved workforce CSV ¦ Stable identity key: employeeId | Authoritative source: Approved workforce CSV ¦ Stable identity key: employeeId | Authoritative source: Approved workforce CSV ¦ Stable identity key: employeeId | Authoritative source: Approved workforce CSV ¦ Stable identity key: employeeId
Event | Trigger | Owner | Main actions | Success verification | Rollback
Joiner | Approved Active record with unique employeeId and a valid startDate that has begun | IAM Operator | Validate, create, assign and enable | Exactly one account with correct attributes and approved group | Disable account and remove partial access
Mover | Approved role, facility or manager change | Manager approves; IAM Operator processes | Snapshot, remove old access, update attributes and add new access | Same account remains; new group is correct and old group is absent | Restore snapshot or keep account disabled
Leaver | Leaving or Inactive status, or expired endDate | Manager or HR triggers; IAM Operator processes | Disable, revoke sessions, remove governed groups and log | Login denied, sessions revoked and groups removed | Keep disabled and escalate any failed cleanup
All workflows | Same approved input is rerun | IAM Operator | Compare current state with desired state before making changes | No duplicate account or membership; log SKIPPED_NO_CHANGE | No rollback required because no change was made

## JML_Validation_Rules
Sunhaven Care JML Validation Rules | Sunhaven Care JML Validation Rules | Sunhaven Care JML Validation Rules
Version: 1.0 ¦ Owner: IAM Project Owner ¦ Rejected records must produce a validation log and no unsafe change | Version: 1.0 ¦ Owner: IAM Project Owner ¦ Rejected records must produce a validation log and no unsafe change | Version: 1.0 ¦ Owner: IAM Project Owner ¦ Rejected records must produce a validation log and no unsafe change
Field | Validation rule | Failure response
employeeId | Required, unique and format SC plus four digits | Reject record
displayName | Required and contains (TEST) | Reject record
employmentType | Permanent, Agency or Contractor | Reject record
jobRole | CareWorker, Nurse, Manager, AgencyWorker, Auditor or IAMOperator | Reject record
facility | Sydney, Brisbane or HeadOffice | Reject record
managerEmployeeId | Must reference an existing active Manager. Manager, Auditor and IAMOperator may be blank as approved top-level lab roles | Reject or manual review
startDate | Valid date in YYYY-MM-DD format | Reject record
endDate | Blank or valid date not earlier than startDate | Reject record
status | Active, Leaving or Inactive | Reject record
Agency endDate | Required for every agency worker | Reject record
userPrincipalName | Must be unique if supplied | Reject record
startDate activation | Account may be enabled only when startDate is today or earlier | Do not enable; log or schedule the record
Agency cross-field rule | If employmentType is Agency, jobRole must be AgencyWorker and endDate is required | Reject record

## JML_Rollback_Plan
Sunhaven Care JML Rollback Plan | Sunhaven Care JML Rollback Plan
Version: 1.0 ¦ Owner: IAM Project Owner ¦ Safety principle: preserve the disabled state when access cleanup is incomplete | Version: 1.0 ¦ Owner: IAM Project Owner ¦ Safety principle: preserve the disabled state when access cleanup is incomplete
Failure | Safe response
Joiner validation fails | Create nothing and log the validation error
Joiner fails after account creation | Disable the account, remove assigned access and request review
Mover cannot find employeeId | Make no changes and request review
Mover fails after removing old access | Restore previous approved groups or disable the account
New role is unknown | Keep current state and reject the change
Leaver session revocation fails | Keep account disabled and alert administrator
Leaver group removal fails | Keep account disabled and retry/manual review
Logging fails | Stop privileged workflow or create local protected fallback record
Duplicate employeeId detected | Process neither record until manually resolved

## Test_Plan
TestID | RequirementID | TestName | TestType | Persona | Preconditions | TestActions | ExpectedResult | EvidenceID | EvidenceType | ActualResult | Status
T01 | REQ-RBAC | Care Worker views assigned resident | Positive | CareWorker | Application is available; Mia is active; RTEST001 is assigned to Mia | Sign in as Mia Carter and open assigned resident RTEST001 | RTEST001 is displayed successfully | EV-T01 | Screenshot |  | NOT RUN
T02 | REQ-RBAC | Care Worker cannot edit clinical note | Negative | CareWorker | Mia is active and assigned the CareWorker role | Sign in as Mia and attempt to edit a clinical note | Access is denied with an Access Denied page or HTTP 403 | EV-T02 | Screenshot and application log |  | NOT RUN
T03 | REQ-RBAC | Nurse edits an assigned clinical note | Positive | Nurse | Noah is active; Nurse role is assigned; resident is assigned to Noah | Sign in as Noah Singh and edit an assigned resident's clinical note | Clinical note is updated and the action is logged | EV-T03 | Screenshot and application log |  | NOT RUN
T04 | REQ-RBAC | Nurse cannot export facility data | Negative | Nurse | Noah is active and assigned the Nurse role | Sign in as Noah and attempt to export facility data | Access is denied with an Access Denied page or HTTP 403 | EV-T04 | Screenshot and application log |  | NOT RUN
T05 | REQ-RBAC | Manager exports data from own facility | Positive | Manager | Ava is active and assigned as Sydney Manager | Sign in as Ava Chen and export Sydney facility data | Export succeeds and the action is logged | EV-T05 | Screenshot and application log |  | NOT RUN
T06 | REQ-RBAC | Manager cannot edit clinical note | Negative | Manager | Ava is active and assigned the Manager role | Sign in as Ava and attempt to edit a clinical note | Access is denied with an Access Denied page or HTTP 403 | EV-T06 | Screenshot and application log |  | NOT RUN
T07 | REQ-RBAC | Active agency worker views assigned resident | Positive | AgencyWorker | Liam is Active; current date is within startDate and endDate; resident is assigned | Sign in as Liam Brooks and open his assigned Sydney resident | Assigned resident is displayed | EV-T07 | Screenshot |  | NOT RUN
T08 | REQ-RBAC | Expired agency worker is denied | Negative | SC1010 Ruby Evans | SC1010 is Inactive and the agency endDate is earlier than the test date | Attempt application access as Ruby Evans | Access is denied because employment has expired | EV-T08 | Screenshot and application log |  | NOT RUN
T09 | REQ-RBAC | Agency worker cannot access another facility | Negative | AgencyWorker | Liam belongs to Sydney and a Brisbane test resident exists | Sign in as Liam and attempt to open the Brisbane resident | Access is denied because the facility does not match | EV-T09 | Screenshot and application log |  | NOT RUN
T10 | REQ-RBAC | Auditor views audit evidence | Positive | Auditor | Zoe is active and assigned the Auditor role | Sign in as Zoe Martin and open the audit-evidence page | Audit evidence is displayed without clinical data | EV-T10 | Screenshot |  | NOT RUN
T11 | REQ-RBAC | Auditor cannot view resident data | Negative | Auditor | Zoe is active and assigned the Auditor role | Sign in as Zoe and attempt to open a resident record | Access is denied with an Access Denied page or HTTP 403 | EV-T11 | Screenshot and application log |  | NOT RUN
T12 | REQ-RBAC | IAM Operator runs approved JML workflow | Positive | IAMOperator | IAM Operator has approved limited administration roles and valid input exists | Run an approved Joiner, Mover, or Leaver operation | Workflow is permitted and produces an audit log | EV-T12 | Command transcript and workflow log |  | NOT RUN
T13 | REQ-RBAC | IAM Operator cannot view resident data | Negative | IAMOperator | IAM Operator account is active | Sign in as IAM Operator and attempt to open resident information | Access is denied with an Access Denied page or HTTP 403 | EV-T13 | Screenshot and application log |  | NOT RUN
T14 | REQ-MFA | Administrator signs in with MFA | Positive Security | IAMAdministrator | IAM Administrator password and Microsoft Authenticator are configured | Sign in as IAM Administrator and complete the MFA request | Administrative access is granted after successful MFA | EV-T14 | Screenshot without MFA secrets |  | NOT RUN
T15 | REQ-MFA | Administrator does not complete MFA | Negative Security | IAMAdministrator | MFA is required for IAM Administrator | Enter the correct password but cancel or do not complete the MFA request | Administrative sign-in is not completed | EV-T15 | Screenshot without MFA secrets |  | NOT RUN
T16 | REQ-AUTH | Normal worker signs in through Entra | Positive Authentication | CareWorker | Mia account is enabled and application registration is configured | Open the application and sign in as Mia using Entra | Mia is authenticated and the application receives her authorised role | EV-T16 | Screenshot and application log |  | NOT RUN
T17 | REQ-AUTH | Disabled worker cannot access application | Negative Authentication | SC1009 Daniel Ortiz | SC1009 exists but the account is disabled in Entra | Attempt a new application sign-in as Daniel Ortiz | Authentication or application access is denied | EV-T17 | Sign-in result and application log |  | NOT RUN
T18 | REQ-JOINER | Valid Joiner account is created | Positive Workflow | SC1008 Isabella Green | SC1008 does not exist; CSV record is approved and complete | Run the Joiner workflow using the SC1008 Active record | Exactly one enabled account is created with correct attributes and group | EV-T18 | User screenshot and workflow log |  | NOT RUN
T19 | REQ-JOINER | Joiner without job role is rejected | Negative Workflow | InvalidJoiner | CSV record contains employeeId but jobRole is blank | Run the Joiner workflow using the invalid record | Record is rejected; validation error is logged; no account is created | EV-T19 | Command transcript and validation log |  | NOT RUN
T20 | REQ-JOINER | Duplicate employee ID is rejected | Negative Workflow | DuplicateJoiner | An Entra identity already exists with the supplied employeeId | Run Joiner workflow using another record with the same employeeId | No second identity is created and duplicate warning is logged | EV-T20 | Command transcript and user search |  | NOT RUN
T21 | REQ-JOINER | New Joiner receives least-privilege group | Positive Security | SC1008 Isabella Green | T18 completed successfully | Open SC1008 group memberships and inspect all assignments | Only SG-CARE-WORKERS and required baseline access are present | EV-T21 | Group-membership screenshot |  | NOT RUN
T22 | REQ-JOINER | Joiner rerun creates no duplicate | Repeatability | SC1008 Isabella Green | T18 completed and SC1008 already exists | Run the identical Joiner input a second time | No duplicate account or membership is created; result is SKIPPED_NO_CHANGE | EV-T22 | Command transcript and workflow log |  | NOT RUN
T23 | REQ-MOVER | Care Worker moves to Nurse | Positive Workflow | SC1001 Mia Carter | Mia exists and currently belongs to SG-CARE-WORKERS | Change Mia's jobRole to Nurse and run the Mover workflow | Same account remains; CareWorker group is removed; Nurse group is added | EV-T23 | Before and after screenshots and log |  | NOT RUN
T24 | REQ-MOVER | Old access is absent after move | Positive Security | SC1001 Mia Carter | T23 completed successfully | Inspect Mia's Entra groups and test application permissions | Mia has Nurse access and no remaining CareWorker group membership | EV-T24 | Group screenshot and application test |  | NOT RUN
T25 | REQ-MOVER | Unknown destination role is rejected | Negative Workflow | SC1001 Mia Carter | Mia has a valid existing role; new CSV jobRole is UnknownRole | Run the Mover workflow with the invalid destination role | Change is rejected and previous approved access remains | EV-T25 | Command transcript and validation log |  | NOT RUN
T26 | REQ-MOVER | Mover rerun creates no duplicate membership | Repeatability | SC1001 Mia Carter | T23 completed and Mia already has the correct Nurse group | Run the same Mover input a second time | No duplicate membership or additional change occurs; result is SKIPPED_NO_CHANGE | EV-T26 | Command transcript and workflow log |  | NOT RUN
T27 | REQ-LEAVER | Leaver account is disabled | Positive Workflow | SC1006 Ethan Khan | Ethan exists; account is enabled; status is Leaving; endDate has passed | Run the Leaver workflow using Ethan's approved Leaving record | Account is disabled immediately | EV-T27 | User-status screenshot and workflow log |  | NOT RUN
T28 | REQ-LEAVER | Leaver sessions and groups are removed | Positive Security | SC1006 Ethan Khan | T27 has begun and Ethan previously had an active business group | Check session-revocation result and Ethan's group memberships | Sessions are revoked and governed business groups are removed | EV-T28 | Group screenshot and workflow log |  | NOT RUN
T29 | REQ-LEAVER | Disabled leaver cannot sign in | Negative Authentication | SC1006 Ethan Khan | T27 completed and Ethan's account is disabled | Attempt a new Entra or application sign-in as Ethan | Sign-in is denied | EV-T29 | Sign-in result screenshot |  | NOT RUN
T30 | REQ-LEAVER | Leaver identity and history are retained | Positive Audit | SC1006 Ethan Khan | Leaver workflow completed | Search for Ethan's user object and related audit events | User object and historical audit evidence remain available | EV-T30 | User screenshot and audit log |  | NOT RUN
T31 | REQ-LEAVER | Leaver rerun is safe | Repeatability | SC1006 Ethan Khan | Ethan is already disabled and governed groups are absent | Run the identical Leaver input a second time | Account remains disabled; no access is restored; result is SKIPPED_NO_CHANGE | EV-T31 | Command transcript and workflow log |  | NOT RUN
T32 | REQ-REVIEW | Access review lists current memberships | Positive Review | Manager | Users and role groups have been created | Generate or open the access-review record for all governed groups | Review shows user role group owner and reviewer decision fields | EV-T32 | Access-review screenshot or CSV |  | NOT RUN
T33 | REQ-REVIEW | Access review detects excessive access | Negative Security | CareWorker | A CareWorker is deliberately placed in SG-MANAGERS in the lab | Run the access review and compare membership with the RBAC matrix | Inappropriate Manager access is identified for removal | EV-T33 | Review CSV and before screenshot |  | NOT RUN
T34 | REQ-REVIEW | Remove-access decision is applied | Positive Workflow | CareWorker | T33 identified inappropriate Manager membership | Approve Remove access and apply the review decision | Incorrect SG-MANAGERS membership is removed and decision is logged | EV-T34 | Before and after screenshots and log |  | NOT RUN
T35 | REQ-AUDIT | Entra audit logs record identity changes | Positive Audit | IAMAdministrator | Joiner Mover and Leaver operations have been executed | Open Entra audit logs and search for user and group changes | Relevant create, update, disable, and membership events are present | EV-T35 | Audit-log screenshot and export |  | NOT RUN
T36 | REQ-AUDIT | Application logs record allowed and denied actions | Positive Audit | IAMOperator | RBAC application tests have been executed | Open the application audit log and search for T01 to T13 actions | Allowed and denied actions show user action time and result | EV-T36 | Application-log screenshot and export |  | NOT RUN
T37 | REQ-PRIVACY | Evidence contains no secrets or real data | Privacy Review | IAMProjectOwner | Test evidence has been collected | Inspect every evidence file for secrets, personal identifiers, and real resident or workforce data | No passwords, tokens, QR codes, recovery codes, or real resident or workforce personal data are present | EV-T37 | Completed privacy checklist |  | NOT RUN

## Requirements_Traceability
RequirementID | Requirement | RelatedTests | PlannedEvidence | Purpose
REQ-RBAC | Role-based least-privilege application access | T01-T13 | EV-T01 to EV-T13 | Prove every business role has permitted and denied actions
REQ-MFA | Multi-factor authentication for privileged administrators | T14-T15 | EV-T14 to EV-T15 | Prove administrator access requires MFA
REQ-AUTH | Entra authentication for application users | T16-T17 | EV-T16 to EV-T17 | Prove active users can authenticate and disabled users are denied
REQ-JOINER | Automated Joiner identity provisioning | T18-T22 | EV-T18 to EV-T22 | Prove valid users are created, while invalid or duplicate records are rejected safely
REQ-MOVER | Automated Mover role and access changes | T23-T26 | EV-T23 to EV-T26 | Prove old access is removed and new approved access is assigned
REQ-LEAVER | Automated Leaver access termination | T27-T31 | EV-T27 to EV-T31 | Prove leaver accounts are disabled, sessions are revoked, and access is removed
REQ-REVIEW | Periodic access review and excessive-access removal | T32-T34 | EV-T32 to EV-T34 | Prove inappropriate access can be identified, reviewed, and removed
REQ-AUDIT | Audit evidence for identity and application activity | T35-T36 | EV-T35 to EV-T36 | Prove important allowed, denied, and administrative actions are recorded
REQ-PRIVACY | Privacy-safe evidence using fictional information | T37 | EV-T37 | Prove submitted evidence contains no secrets or real resident information
REQ-SAFETY | Wrong-tenant and fail-closed automation protection | TC-014 | Final wrong-tenant guard-test transcript | Prove automation validates the explicit tenant before attempting directory writes

## Evidence_Index
EvidenceID | TestID | PlannedFileName | EvidenceType | MaskingRequired | Status
EV-T01 | T01 | EV-T01-Evidence | Screenshot | Yes | NOT CAPTURED
EV-T02 | T02 | EV-T02-Evidence | Screenshot and application log | Yes | NOT CAPTURED
EV-T03 | T03 | EV-T03-Evidence | Screenshot and application log | Yes | NOT CAPTURED
EV-T04 | T04 | EV-T04-Evidence | Screenshot and application log | Yes | NOT CAPTURED
EV-T05 | T05 | EV-T05-Evidence | Screenshot and application log | Yes | NOT CAPTURED
EV-T06 | T06 | EV-T06-Evidence | Screenshot and application log | Yes | NOT CAPTURED
EV-T07 | T07 | EV-T07-Evidence | Screenshot | Yes | NOT CAPTURED
EV-T08 | T08 | EV-T08-Evidence | Screenshot and application log | Yes | NOT CAPTURED
EV-T09 | T09 | EV-T09-Evidence | Screenshot and application log | Yes | NOT CAPTURED
EV-T10 | T10 | EV-T10-Evidence | Screenshot | Yes | NOT CAPTURED
EV-T11 | T11 | EV-T11-Evidence | Screenshot and application log | Yes | NOT CAPTURED
EV-T12 | T12 | EV-T12-Evidence | Command transcript and workflow log | Yes | NOT CAPTURED
EV-T13 | T13 | EV-T13-Evidence | Screenshot and application log | Yes | NOT CAPTURED
EV-T14 | T14 | EV-T14-Evidence | Screenshot without MFA secrets | Yes | NOT CAPTURED
EV-T15 | T15 | EV-T15-Evidence | Screenshot without MFA secrets | Yes | NOT CAPTURED
EV-T16 | T16 | EV-T16-Evidence | Screenshot and application log | Yes | NOT CAPTURED
EV-T17 | T17 | EV-T17-Evidence | Sign-in result and application log | Yes | NOT CAPTURED
EV-T18 | T18 | EV-T18-Evidence | User screenshot and workflow log | Yes | NOT CAPTURED
EV-T19 | T19 | EV-T19-Evidence | Command transcript and validation log | Yes | NOT CAPTURED
EV-T20 | T20 | EV-T20-Evidence | Command transcript and user search | Yes | NOT CAPTURED
EV-T21 | T21 | EV-T21-Evidence | Group-membership screenshot | Yes | NOT CAPTURED
EV-T22 | T22 | EV-T22-Evidence | Command transcript and workflow log | Yes | NOT CAPTURED
EV-T23 | T23 | EV-T23-Evidence | Before and after screenshots and log | Yes | NOT CAPTURED
EV-T24 | T24 | EV-T24-Evidence | Group screenshot and application test | Yes | NOT CAPTURED
EV-T25 | T25 | EV-T25-Evidence | Command transcript and validation log | Yes | NOT CAPTURED
EV-T26 | T26 | EV-T26-Evidence | Command transcript and workflow log | Yes | NOT CAPTURED
EV-T27 | T27 | EV-T27-Evidence | User-status screenshot and workflow log | Yes | NOT CAPTURED
EV-T28 | T28 | EV-T28-Evidence | Group screenshot and workflow log | Yes | NOT CAPTURED
EV-T29 | T29 | EV-T29-Evidence | Sign-in result screenshot | Yes | NOT CAPTURED
EV-T30 | T30 | EV-T30-Evidence | User screenshot and audit log | Yes | NOT CAPTURED
EV-T31 | T31 | EV-T31-Evidence | Command transcript and workflow log | Yes | NOT CAPTURED
EV-T32 | T32 | EV-T32-Evidence | Access-review screenshot or CSV | Yes | NOT CAPTURED
EV-T33 | T33 | EV-T33-Evidence | Review CSV and before screenshot | Yes | NOT CAPTURED
EV-T34 | T34 | EV-T34-Evidence | Before and after screenshots and log | Yes | NOT CAPTURED
EV-T35 | T35 | EV-T35-Evidence | Audit-log screenshot and export | Yes | NOT CAPTURED
EV-T36 | T36 | EV-T36-Evidence | Application-log screenshot and export | Yes | NOT CAPTURED
EV-T37 | T37 | EV-T37-Evidence | Completed privacy checklist | Yes | NOT CAPTURED